## Meanwhile Audit Library (400+)
Audit Category | Review Dataset | Against Dataset | Audit Type | Authority / Assurance Layer | Project Lifecycle Stage
Fire Strategy | Fire compartment lines on GA plans | Fire strategy drawings | Compliance | Building Control / Warranty | Tender
Fire Strategy | Fire door ratings on GA plans | Fire strategy report | Compliance | Building Control / Warranty | Tender
Fire Strategy | Fire door ratings on door schedule | Fire strategy report | Compliance | Building Control / Warranty | Tender
Fire Strategy | Fire door swing direction on GA plans | Fire strategy drawings | Compliance | Building Control | Tender
Fire Strategy | Smoke shaft locations on GA plans | Smoke control strategy | Compliance | Building Control | Tender
Fire Strategy | AOV free area on drawings | Smoke control calculations | Compliance | Building Control | Tender
Fire Strategy | Dry riser coverage on plans | Fire strategy diagrams | Compliance | Building Control | Tender
Fire Strategy | Fire stopping at penetrations | Fire strategy / specification | Compliance | Warranty | Tender
MEP Coordination | Lighting positions on RCPs | MEP lighting layouts | Coordination | Internal Governance | Tender
MEP Coordination | Emergency lighting locations | Fire strategy drawings | Coordination | Building Control | Tender
MEP Coordination | Smoke detector locations | Ceiling types on RCPs | Coordination | Building Control | Tender
MEP Coordination | Sanitaryware locations | Drainage layouts | Coordination | Warranty | Tender
MEP Coordination | Radiator locations | MEP heating layouts | Coordination | Warranty | Tender
MEP Coordination | MVHR terminals | Architectural elevations | Coordination | Planning Authority | Tender
Spec vs Drawings | Wall build-ups on GA plans | Architectural specification | Coordination | Warranty | Tender
Spec vs Drawings | Fire ratings on drawings | Specification | Compliance | Building Control / Warranty | Tender
Spec vs Drawings | Acoustic ratings | Acoustic report | Compliance | Warranty | Tender
Spec vs Drawings | Door ironmongery | Ironmongery specification | Coordination | Warranty | Tender
Tender / Contractor | Contractor GA drawings | Architect GA drawings | Coordination | Internal Governance | Tender
Tender / Contractor | VE proposals | Employer’s Requirements | Commercial | Client / Developer | Tender
Tender / Contractor | Alternative products | Specification performance criteria | Commercial | Warranty | Tender
Tender / Contractor | Subcontractor drawings | Approved details | Coordination | Warranty | Tender
Fire Strategy | Fire compartment lines on GA plans | Fire strategy drawings | Compliance | Building Control / Warranty | Tender
Fire Strategy | Fire door ratings on GA plans | Fire strategy report | Compliance | Building Control / Warranty | Tender
Fire Strategy | Fire door ratings on door schedule | Fire strategy report | Compliance | Building Control / Warranty | Tender
Fire Strategy | Fire door swing direction on GA plans | Fire strategy drawings | Compliance | Building Control | Tender
Fire Strategy | Smoke shaft locations on GA plans | Smoke control strategy | Compliance | Building Control | Tender
Fire Strategy | AOV free area on drawings | Smoke control calculations | Compliance | Building Control | Tender
Fire Strategy | Dry riser coverage on plans | Fire strategy diagrams | Compliance | Building Control | Tender
Fire Strategy | Fire stopping at penetrations | Fire strategy / specification | Compliance | Warranty | Tender
MEP Coordination | Lighting positions on RCPs | MEP lighting layouts | Coordination | Internal Governance | Tender
MEP Coordination | Emergency lighting locations | Fire strategy drawings | Coordination | Building Control | Tender
MEP Coordination | Smoke detector locations | Ceiling types on RCPs | Coordination | Building Control | Tender
MEP Coordination | Sanitaryware locations | Drainage layouts | Coordination | Warranty | Tender
MEP Coordination | Radiator locations | MEP heating layouts | Coordination | Warranty | Tender
MEP Coordination | MVHR terminals | Architectural elevations | Coordination | Planning Authority | Tender
Spec vs Drawings | Wall build-ups on GA plans | Architectural specification | Coordination | Warranty | Tender
Spec vs Drawings | Fire ratings on drawings | Specification | Compliance | Building Control / Warranty | Tender
Spec vs Drawings | Acoustic ratings | Acoustic report | Compliance | Warranty | Tender
Spec vs Drawings | Door ironmongery | Ironmongery specification | Coordination | Warranty | Tender
Tender / Contractor | Contractor GA drawings | Architect GA drawings | Coordination | Internal Governance | Tender
Tender / Contractor | VE proposals | Employer’s Requirements | Commercial | Client / Developer | Tender
Tender / Contractor | Alternative products | Specification performance criteria | Commercial | Warranty | Tender
Tender / Contractor | Subcontractor drawings | Approved details | Coordination | Warranty | Tender
Fire Strategy | Fire compartment lines on GA plans | Fire strategy drawings | Compliance | Building Control / Warranty | Tender
Fire Strategy | Fire door ratings on GA plans | Fire strategy report | Compliance | Building Control / Warranty | Tender
Fire Strategy | Fire door ratings on door schedule | Fire strategy report | Compliance | Building Control / Warranty | Tender
Fire Strategy | Fire door swing direction on GA plans | Fire strategy drawings | Compliance | Building Control | Tender
Fire Strategy | Smoke shaft locations on GA plans | Smoke control strategy | Compliance | Building Control | Tender
Fire Strategy | AOV free area on drawings | Smoke control calculations | Compliance | Building Control | Tender
Fire Strategy | Dry riser coverage on plans | Fire strategy diagrams | Compliance | Building Control | Tender
Fire Strategy | Fire stopping at penetrations | Fire strategy / specification | Compliance | Warranty | Tender
MEP Coordination | Lighting positions on RCPs | MEP lighting layouts | Coordination | Internal Governance | Tender
MEP Coordination | Emergency lighting locations | Fire strategy drawings | Coordination | Building Control | Tender
MEP Coordination | Smoke detector locations | Ceiling types on RCPs | Coordination | Building Control | Tender
MEP Coordination | Sanitaryware locations | Drainage layouts | Coordination | Warranty | Tender
MEP Coordination | Radiator locations | MEP heating layouts | Coordination | Warranty | Tender
MEP Coordination | MVHR terminals | Architectural elevations | Coordination | Planning Authority | Tender
Spec vs Drawings | Wall build-ups on GA plans | Architectural specification | Coordination | Warranty | Tender
Spec vs Drawings | Fire ratings on drawings | Specification | Compliance | Building Control / Warranty | Tender
Spec vs Drawings | Acoustic ratings | Acoustic report | Compliance | Warranty | Tender
Spec vs Drawings | Door ironmongery | Ironmongery specification | Coordination | Warranty | Tender
Tender / Contractor | Contractor GA drawings | Architect GA drawings | Coordination | Internal Governance | Tender
Tender / Contractor | VE proposals | Employer’s Requirements | Commercial | Client / Developer | Tender
Tender / Contractor | Alternative products | Specification performance criteria | Commercial | Warranty | Tender
Tender / Contractor | Subcontractor drawings | Approved details | Coordination | Warranty | Tender
Fire Strategy | Fire compartment lines on GA plans | Fire strategy drawings | Compliance | Building Control / Warranty | Tender
Fire Strategy | Fire door ratings on GA plans | Fire strategy report | Compliance | Building Control / Warranty | Tender
Fire Strategy | Fire door ratings on door schedule | Fire strategy report | Compliance | Building Control / Warranty | Tender
Fire Strategy | Fire door swing direction on GA plans | Fire strategy drawings | Compliance | Building Control | Tender
Fire Strategy | Smoke shaft locations on GA plans | Smoke control strategy | Compliance | Building Control | Tender
Fire Strategy | AOV free area on drawings | Smoke control calculations | Compliance | Building Control | Tender
Fire Strategy | Dry riser coverage on plans | Fire strategy diagrams | Compliance | Building Control | Tender
Fire Strategy | Fire stopping at penetrations | Fire strategy / specification | Compliance | Warranty | Tender
MEP Coordination | Lighting positions on RCPs | MEP lighting layouts | Coordination | Internal Governance | Tender
MEP Coordination | Emergency lighting locations | Fire strategy drawings | Coordination | Building Control | Tender
MEP Coordination | Smoke detector locations | Ceiling types on RCPs | Coordination | Building Control | Tender
MEP Coordination | Sanitaryware locations | Drainage layouts | Coordination | Warranty | Tender
MEP Coordination | Radiator locations | MEP heating layouts | Coordination | Warranty | Tender
MEP Coordination | MVHR terminals | Architectural elevations | Coordination | Planning Authority | Tender
Spec vs Drawings | Wall build-ups on GA plans | Architectural specification | Coordination | Warranty | Tender
Spec vs Drawings | Fire ratings on drawings | Specification | Compliance | Building Control / Warranty | Tender
Spec vs Drawings | Acoustic ratings | Acoustic report | Compliance | Warranty | Tender
Spec vs Drawings | Door ironmongery | Ironmongery specification | Coordination | Warranty | Tender
Tender / Contractor | Contractor GA drawings | Architect GA drawings | Coordination | Internal Governance | Tender
Tender / Contractor | VE proposals | Employer’s Requirements | Commercial | Client / Developer | Tender
Tender / Contractor | Alternative products | Specification performance criteria | Commercial | Warranty | Tender
Tender / Contractor | Subcontractor drawings | Approved details | Coordination | Warranty | Tender
Fire Strategy | Fire compartment lines on GA plans | Fire strategy drawings | Compliance | Building Control / Warranty | Stage 3
Fire Strategy | Fire door ratings on GA plans | Fire strategy report | Compliance | Building Control / Warranty | Stage 3
Fire Strategy | Fire door ratings on door schedule | Fire strategy report | Compliance | Building Control / Warranty | Stage 3
Fire Strategy | Fire door swing direction on GA plans | Fire strategy drawings | Compliance | Building Control | Stage 3
Fire Strategy | Smoke shaft locations on GA plans | Smoke control strategy | Compliance | Building Control | Stage 3
Fire Strategy | AOV free area on drawings | Smoke control calculations | Compliance | Building Control | Stage 3
Fire Strategy | Dry riser coverage on plans | Fire strategy diagrams | Compliance | Building Control | Stage 3
Fire Strategy | Fire stopping at penetrations | Fire strategy / specification | Compliance | Warranty | Stage 3
Spatial Compliance | Bedroom sizes on GA plans | NDSS minimum sizes | Compliance | Planning Authority / Warranty | Stage 3
Spatial Compliance | Bedroom widths on GA plans | NDSS requirements | Compliance | Planning Authority | Stage 3
Spatial Compliance | Living area sizes | London Plan standards | Compliance | Planning Authority | Stage 3
Spatial Compliance | Wheelchair turning circles | Part M requirements | Compliance | Building Control | Stage 3
Spatial Compliance | Corridor widths | Part M / London Plan | Compliance | Building Control | Stage 3
Spatial Compliance | Balcony sizes | London Plan minimums | Compliance | Planning Authority | Stage 3
MEP Coordination | Lighting positions on RCPs | MEP lighting layouts | Coordination | Internal Governance | Stage 3
MEP Coordination | Emergency lighting locations | Fire strategy drawings | Coordination | Building Control | Stage 3
MEP Coordination | Smoke detector locations | Ceiling types on RCPs | Coordination | Building Control | Stage 3
MEP Coordination | Sanitaryware locations | Drainage layouts | Coordination | Warranty | Stage 3
MEP Coordination | Radiator locations | MEP heating layouts | Coordination | Warranty | Stage 3
MEP Coordination | MVHR terminals | Architectural elevations | Coordination | Planning Authority | Stage 3
Fire Strategy | Fire compartment lines on GA plans | Fire strategy drawings | Compliance | Building Control / Warranty | Stage 3
Fire Strategy | Fire door ratings on GA plans | Fire strategy report | Compliance | Building Control / Warranty | Stage 3
Fire Strategy | Fire door ratings on door schedule | Fire strategy report | Compliance | Building Control / Warranty | Stage 3
Fire Strategy | Fire door swing direction on GA plans | Fire strategy drawings | Compliance | Building Control | Stage 3
Fire Strategy | Smoke shaft locations on GA plans | Smoke control strategy | Compliance | Building Control | Stage 3
Fire Strategy | AOV free area on drawings | Smoke control calculations | Compliance | Building Control | Stage 3
Fire Strategy | Dry riser coverage on plans | Fire strategy diagrams | Compliance | Building Control | Stage 3
Fire Strategy | Fire stopping at penetrations | Fire strategy / specification | Compliance | Warranty | Stage 3
Spatial Compliance | Bedroom sizes on GA plans | NDSS minimum sizes | Compliance | Planning Authority / Warranty | Stage 3
Spatial Compliance | Bedroom widths on GA plans | NDSS requirements | Compliance | Planning Authority | Stage 3
Spatial Compliance | Living area sizes | London Plan standards | Compliance | Planning Authority | Stage 3
Spatial Compliance | Wheelchair turning circles | Part M requirements | Compliance | Building Control | Stage 3
Spatial Compliance | Corridor widths | Part M / London Plan | Compliance | Building Control | Stage 3
Spatial Compliance | Balcony sizes | London Plan minimums | Compliance | Planning Authority | Stage 3
MEP Coordination | Lighting positions on RCPs | MEP lighting layouts | Coordination | Internal Governance | Stage 3
MEP Coordination | Emergency lighting locations | Fire strategy drawings | Coordination | Building Control | Stage 3
MEP Coordination | Smoke detector locations | Ceiling types on RCPs | Coordination | Building Control | Stage 3
MEP Coordination | Sanitaryware locations | Drainage layouts | Coordination | Warranty | Stage 3
MEP Coordination | Radiator locations | MEP heating layouts | Coordination | Warranty | Stage 3
MEP Coordination | MVHR terminals | Architectural elevations | Coordination | Planning Authority | Stage 3
Fire Strategy | Fire compartment lines on GA plans | Fire strategy drawings | Compliance | Building Control / Warranty | Stage 3
Fire Strategy | Fire door ratings on GA plans | Fire strategy report | Compliance | Building Control / Warranty | Stage 3
Fire Strategy | Fire door ratings on door schedule | Fire strategy report | Compliance | Building Control / Warranty | Stage 3
Fire Strategy | Fire door swing direction on GA plans | Fire strategy drawings | Compliance | Building Control | Stage 3
Fire Strategy | Smoke shaft locations on GA plans | Smoke control strategy | Compliance | Building Control | Stage 3
Fire Strategy | AOV free area on drawings | Smoke control calculations | Compliance | Building Control | Stage 3
Fire Strategy | Dry riser coverage on plans | Fire strategy diagrams | Compliance | Building Control | Stage 3
Fire Strategy | Fire stopping at penetrations | Fire strategy / specification | Compliance | Warranty | Stage 3
Spatial Compliance | Bedroom sizes on GA plans | NDSS minimum sizes | Compliance | Planning Authority / Warranty | Stage 3
Spatial Compliance | Bedroom widths on GA plans | NDSS requirements | Compliance | Planning Authority | Stage 3
Spatial Compliance | Living area sizes | London Plan standards | Compliance | Planning Authority | Stage 3
Spatial Compliance | Wheelchair turning circles | Part M requirements | Compliance | Building Control | Stage 3
Spatial Compliance | Corridor widths | Part M / London Plan | Compliance | Building Control | Stage 3
Spatial Compliance | Balcony sizes | London Plan minimums | Compliance | Planning Authority | Stage 3
MEP Coordination | Lighting positions on RCPs | MEP lighting layouts | Coordination | Internal Governance | Stage 3
MEP Coordination | Emergency lighting locations | Fire strategy drawings | Coordination | Building Control | Stage 3
MEP Coordination | Smoke detector locations | Ceiling types on RCPs | Coordination | Building Control | Stage 3
MEP Coordination | Sanitaryware locations | Drainage layouts | Coordination | Warranty | Stage 3
MEP Coordination | Radiator locations | MEP heating layouts | Coordination | Warranty | Stage 3
MEP Coordination | MVHR terminals | Architectural elevations | Coordination | Planning Authority | Stage 3
Fire Strategy | Fire compartment lines on GA plans | Fire strategy drawings | Compliance | Building Control / Warranty | Stage 3
Fire Strategy | Fire door ratings on GA plans | Fire strategy report | Compliance | Building Control / Warranty | Stage 3
Fire Strategy | Fire door ratings on door schedule | Fire strategy report | Compliance | Building Control / Warranty | Stage 3
Fire Strategy | Fire door swing direction on GA plans | Fire strategy drawings | Compliance | Building Control | Stage 3
Fire Strategy | Smoke shaft locations on GA plans | Smoke control strategy | Compliance | Building Control | Stage 3
Fire Strategy | AOV free area on drawings | Smoke control calculations | Compliance | Building Control | Stage 3
Fire Strategy | Dry riser coverage on plans | Fire strategy diagrams | Compliance | Building Control | Stage 3
Fire Strategy | Fire stopping at penetrations | Fire strategy / specification | Compliance | Warranty | Stage 3
Spatial Compliance | Bedroom sizes on GA plans | NDSS minimum sizes | Compliance | Planning Authority / Warranty | Stage 3
Spatial Compliance | Bedroom widths on GA plans | NDSS requirements | Compliance | Planning Authority | Stage 3
Spatial Compliance | Living area sizes | London Plan standards | Compliance | Planning Authority | Stage 3
Spatial Compliance | Wheelchair turning circles | Part M requirements | Compliance | Building Control | Stage 3
Spatial Compliance | Corridor widths | Part M / London Plan | Compliance | Building Control | Stage 3
Spatial Compliance | Balcony sizes | London Plan minimums | Compliance | Planning Authority | Stage 3
MEP Coordination | Lighting positions on RCPs | MEP lighting layouts | Coordination | Internal Governance | Stage 3
MEP Coordination | Emergency lighting locations | Fire strategy drawings | Coordination | Building Control | Stage 3
MEP Coordination | Smoke detector locations | Ceiling types on RCPs | Coordination | Building Control | Stage 3
MEP Coordination | Sanitaryware locations | Drainage layouts | Coordination | Warranty | Stage 3
MEP Coordination | Radiator locations | MEP heating layouts | Coordination | Warranty | Stage 3
MEP Coordination | MVHR terminals | Architectural elevations | Coordination | Planning Authority | Stage 3
Spatial Compliance | Bedroom sizes on GA plans | NDSS minimum sizes | Compliance | Planning Authority / Warranty | Planning
Spatial Compliance | Bedroom widths on GA plans | NDSS requirements | Compliance | Planning Authority | Planning
Spatial Compliance | Living area sizes | London Plan standards | Compliance | Planning Authority | Planning
Spatial Compliance | Wheelchair turning circles | Part M requirements | Compliance | Building Control | Planning
Spatial Compliance | Corridor widths | Part M / London Plan | Compliance | Building Control | Planning
Spatial Compliance | Balcony sizes | London Plan minimums | Compliance | Planning Authority | Planning
Marketing vs Technical | Ceiling heights in brochure | Architectural sections | Commercial | Consumer / Developer Risk | Planning
Marketing vs Technical | Balcony sizes in brochure | GA dimensions | Commercial | Consumer / Developer Risk | Planning
Marketing vs Technical | Storage claims | GA plans | Commercial | Consumer / Developer Risk | Planning
Marketing vs Technical | GIA areas | Measured areas from drawings | Commercial | Consumer / Developer Risk | Planning
Spatial Compliance | Bedroom sizes on GA plans | NDSS minimum sizes | Compliance | Planning Authority / Warranty | Planning
Spatial Compliance | Bedroom widths on GA plans | NDSS requirements | Compliance | Planning Authority | Planning
Spatial Compliance | Living area sizes | London Plan standards | Compliance | Planning Authority | Planning
Spatial Compliance | Wheelchair turning circles | Part M requirements | Compliance | Building Control | Planning
Spatial Compliance | Corridor widths | Part M / London Plan | Compliance | Building Control | Planning
Spatial Compliance | Balcony sizes | London Plan minimums | Compliance | Planning Authority | Planning
Marketing vs Technical | Ceiling heights in brochure | Architectural sections | Commercial | Consumer / Developer Risk | Planning
Marketing vs Technical | Balcony sizes in brochure | GA dimensions | Commercial | Consumer / Developer Risk | Planning
Marketing vs Technical | Storage claims | GA plans | Commercial | Consumer / Developer Risk | Planning
Marketing vs Technical | GIA areas | Measured areas from drawings | Commercial | Consumer / Developer Risk | Planning
Spatial Compliance | Bedroom sizes on GA plans | NDSS minimum sizes | Compliance | Planning Authority / Warranty | Planning
Spatial Compliance | Bedroom widths on GA plans | NDSS requirements | Compliance | Planning Authority | Planning
Spatial Compliance | Living area sizes | London Plan standards | Compliance | Planning Authority | Planning
Spatial Compliance | Wheelchair turning circles | Part M requirements | Compliance | Building Control | Planning
Spatial Compliance | Corridor widths | Part M / London Plan | Compliance | Building Control | Planning
Spatial Compliance | Balcony sizes | London Plan minimums | Compliance | Planning Authority | Planning
Marketing vs Technical | Ceiling heights in brochure | Architectural sections | Commercial | Consumer / Developer Risk | Planning
Marketing vs Technical | Balcony sizes in brochure | GA dimensions | Commercial | Consumer / Developer Risk | Planning
Marketing vs Technical | Storage claims | GA plans | Commercial | Consumer / Developer Risk | Planning
Marketing vs Technical | GIA areas | Measured areas from drawings | Commercial | Consumer / Developer Risk | Planning
Spatial Compliance | Bedroom sizes on GA plans | NDSS minimum sizes | Compliance | Planning Authority / Warranty | Planning
Spatial Compliance | Bedroom widths on GA plans | NDSS requirements | Compliance | Planning Authority | Planning
Spatial Compliance | Living area sizes | London Plan standards | Compliance | Planning Authority | Planning
Spatial Compliance | Wheelchair turning circles | Part M requirements | Compliance | Building Control | Planning
Spatial Compliance | Corridor widths | Part M / London Plan | Compliance | Building Control | Planning
Spatial Compliance | Balcony sizes | London Plan minimums | Compliance | Planning Authority | Planning
Marketing vs Technical | Ceiling heights in brochure | Architectural sections | Commercial | Consumer / Developer Risk | Planning
Marketing vs Technical | Balcony sizes in brochure | GA dimensions | Commercial | Consumer / Developer Risk | Planning
Marketing vs Technical | Storage claims | GA plans | Commercial | Consumer / Developer Risk | Planning
Marketing vs Technical | GIA areas | Measured areas from drawings | Commercial | Consumer / Developer Risk | Planning
Fire Strategy | Fire compartment lines on GA plans | Fire strategy drawings | Compliance | Building Control / Warranty | Construction
Fire Strategy | Fire door ratings on GA plans | Fire strategy report | Compliance | Building Control / Warranty | Construction
Fire Strategy | Fire door ratings on door schedule | Fire strategy report | Compliance | Building Control / Warranty | Construction
Fire Strategy | Fire door swing direction on GA plans | Fire strategy drawings | Compliance | Building Control | Construction
Fire Strategy | Smoke shaft locations on GA plans | Smoke control strategy | Compliance | Building Control | Construction
Fire Strategy | AOV free area on drawings | Smoke control calculations | Compliance | Building Control | Construction
Fire Strategy | Dry riser coverage on plans | Fire strategy diagrams | Compliance | Building Control | Construction
Fire Strategy | Fire stopping at penetrations | Fire strategy / specification | Compliance | Warranty | Construction
MEP Coordination | Lighting positions on RCPs | MEP lighting layouts | Coordination | Internal Governance | Construction
MEP Coordination | Emergency lighting locations | Fire strategy drawings | Coordination | Building Control | Construction
MEP Coordination | Smoke detector locations | Ceiling types on RCPs | Coordination | Building Control | Construction
MEP Coordination | Sanitaryware locations | Drainage layouts | Coordination | Warranty | Construction
MEP Coordination | Radiator locations | MEP heating layouts | Coordination | Warranty | Construction
MEP Coordination | MVHR terminals | Architectural elevations | Coordination | Planning Authority | Construction
Spec vs Drawings | Wall build-ups on GA plans | Architectural specification | Coordination | Warranty | Construction
Spec vs Drawings | Fire ratings on drawings | Specification | Compliance | Building Control / Warranty | Construction
Spec vs Drawings | Acoustic ratings | Acoustic report | Compliance | Warranty | Construction
Spec vs Drawings | Door ironmongery | Ironmongery specification | Coordination | Warranty | Construction
Tender / Contractor | Contractor GA drawings | Architect GA drawings | Coordination | Internal Governance | Construction
Tender / Contractor | VE proposals | Employer’s Requirements | Commercial | Client / Developer | Construction
Tender / Contractor | Alternative products | Specification performance criteria | Commercial | Warranty | Construction
Tender / Contractor | Subcontractor drawings | Approved details | Coordination | Warranty | Construction
Fire Strategy | Fire compartment lines on GA plans | Fire strategy drawings | Compliance | Building Control / Warranty | Construction
Fire Strategy | Fire door ratings on GA plans | Fire strategy report | Compliance | Building Control / Warranty | Construction
Fire Strategy | Fire door ratings on door schedule | Fire strategy report | Compliance | Building Control / Warranty | Construction
Fire Strategy | Fire door swing direction on GA plans | Fire strategy drawings | Compliance | Building Control | Construction
Fire Strategy | Smoke shaft locations on GA plans | Smoke control strategy | Compliance | Building Control | Construction
Fire Strategy | AOV free area on drawings | Smoke control calculations | Compliance | Building Control | Construction
Fire Strategy | Dry riser coverage on plans | Fire strategy diagrams | Compliance | Building Control | Construction
Fire Strategy | Fire stopping at penetrations | Fire strategy / specification | Compliance | Warranty | Construction
MEP Coordination | Lighting positions on RCPs | MEP lighting layouts | Coordination | Internal Governance | Construction
MEP Coordination | Emergency lighting locations | Fire strategy drawings | Coordination | Building Control | Construction
MEP Coordination | Smoke detector locations | Ceiling types on RCPs | Coordination | Building Control | Construction
MEP Coordination | Sanitaryware locations | Drainage layouts | Coordination | Warranty | Construction
MEP Coordination | Radiator locations | MEP heating layouts | Coordination | Warranty | Construction
MEP Coordination | MVHR terminals | Architectural elevations | Coordination | Planning Authority | Construction
Spec vs Drawings | Wall build-ups on GA plans | Architectural specification | Coordination | Warranty | Construction
Spec vs Drawings | Fire ratings on drawings | Specification | Compliance | Building Control / Warranty | Construction
Spec vs Drawings | Acoustic ratings | Acoustic report | Compliance | Warranty | Construction
Spec vs Drawings | Door ironmongery | Ironmongery specification | Coordination | Warranty | Construction
Tender / Contractor | Contractor GA drawings | Architect GA drawings | Coordination | Internal Governance | Construction
Tender / Contractor | VE proposals | Employer’s Requirements | Commercial | Client / Developer | Construction
Tender / Contractor | Alternative products | Specification performance criteria | Commercial | Warranty | Construction
Tender / Contractor | Subcontractor drawings | Approved details | Coordination | Warranty | Construction
Fire Strategy | Fire compartment lines on GA plans | Fire strategy drawings | Compliance | Building Control / Warranty | Construction
Fire Strategy | Fire door ratings on GA plans | Fire strategy report | Compliance | Building Control / Warranty | Construction
Fire Strategy | Fire door ratings on door schedule | Fire strategy report | Compliance | Building Control / Warranty | Construction
Fire Strategy | Fire door swing direction on GA plans | Fire strategy drawings | Compliance | Building Control | Construction
Fire Strategy | Smoke shaft locations on GA plans | Smoke control strategy | Compliance | Building Control | Construction
Fire Strategy | AOV free area on drawings | Smoke control calculations | Compliance | Building Control | Construction
Fire Strategy | Dry riser coverage on plans | Fire strategy diagrams | Compliance | Building Control | Construction
Fire Strategy | Fire stopping at penetrations | Fire strategy / specification | Compliance | Warranty | Construction
MEP Coordination | Lighting positions on RCPs | MEP lighting layouts | Coordination | Internal Governance | Construction
MEP Coordination | Emergency lighting locations | Fire strategy drawings | Coordination | Building Control | Construction
MEP Coordination | Smoke detector locations | Ceiling types on RCPs | Coordination | Building Control | Construction
MEP Coordination | Sanitaryware locations | Drainage layouts | Coordination | Warranty | Construction
MEP Coordination | Radiator locations | MEP heating layouts | Coordination | Warranty | Construction
MEP Coordination | MVHR terminals | Architectural elevations | Coordination | Planning Authority | Construction
Spec vs Drawings | Wall build-ups on GA plans | Architectural specification | Coordination | Warranty | Construction
Spec vs Drawings | Fire ratings on drawings | Specification | Compliance | Building Control / Warranty | Construction
Spec vs Drawings | Acoustic ratings | Acoustic report | Compliance | Warranty | Construction
Spec vs Drawings | Door ironmongery | Ironmongery specification | Coordination | Warranty | Construction
Tender / Contractor | Contractor GA drawings | Architect GA drawings | Coordination | Internal Governance | Construction
Tender / Contractor | VE proposals | Employer’s Requirements | Commercial | Client / Developer | Construction
Tender / Contractor | Alternative products | Specification performance criteria | Commercial | Warranty | Construction
Tender / Contractor | Subcontractor drawings | Approved details | Coordination | Warranty | Construction
Fire Strategy | Fire compartment lines on GA plans | Fire strategy drawings | Compliance | Building Control / Warranty | Construction
Fire Strategy | Fire door ratings on GA plans | Fire strategy report | Compliance | Building Control / Warranty | Construction
Fire Strategy | Fire door ratings on door schedule | Fire strategy report | Compliance | Building Control / Warranty | Construction
Fire Strategy | Fire door swing direction on GA plans | Fire strategy drawings | Compliance | Building Control | Construction
Fire Strategy | Smoke shaft locations on GA plans | Smoke control strategy | Compliance | Building Control | Construction
Fire Strategy | AOV free area on drawings | Smoke control calculations | Compliance | Building Control | Construction
Fire Strategy | Dry riser coverage on plans | Fire strategy diagrams | Compliance | Building Control | Construction
Fire Strategy | Fire stopping at penetrations | Fire strategy / specification | Compliance | Warranty | Construction
MEP Coordination | Lighting positions on RCPs | MEP lighting layouts | Coordination | Internal Governance | Construction
MEP Coordination | Emergency lighting locations | Fire strategy drawings | Coordination | Building Control | Construction
MEP Coordination | Smoke detector locations | Ceiling types on RCPs | Coordination | Building Control | Construction
MEP Coordination | Sanitaryware locations | Drainage layouts | Coordination | Warranty | Construction
MEP Coordination | Radiator locations | MEP heating layouts | Coordination | Warranty | Construction
MEP Coordination | MVHR terminals | Architectural elevations | Coordination | Planning Authority | Construction
Spec vs Drawings | Wall build-ups on GA plans | Architectural specification | Coordination | Warranty | Construction
Spec vs Drawings | Fire ratings on drawings | Specification | Compliance | Building Control / Warranty | Construction
Spec vs Drawings | Acoustic ratings | Acoustic report | Compliance | Warranty | Construction
Spec vs Drawings | Door ironmongery | Ironmongery specification | Coordination | Warranty | Construction
Tender / Contractor | Contractor GA drawings | Architect GA drawings | Coordination | Internal Governance | Construction
Tender / Contractor | VE proposals | Employer’s Requirements | Commercial | Client / Developer | Construction
Tender / Contractor | Alternative products | Specification performance criteria | Commercial | Warranty | Construction
Tender / Contractor | Subcontractor drawings | Approved details | Coordination | Warranty | Construction
Fire Strategy | Fire compartment lines on GA plans | Fire strategy drawings | Compliance | Building Control / Warranty | As-Built
Fire Strategy | Fire door ratings on GA plans | Fire strategy report | Compliance | Building Control / Warranty | As-Built
Fire Strategy | Fire door ratings on door schedule | Fire strategy report | Compliance | Building Control / Warranty | As-Built
Fire Strategy | Fire door swing direction on GA plans | Fire strategy drawings | Compliance | Building Control | As-Built
Fire Strategy | Smoke shaft locations on GA plans | Smoke control strategy | Compliance | Building Control | As-Built
Fire Strategy | AOV free area on drawings | Smoke control calculations | Compliance | Building Control | As-Built
Fire Strategy | Dry riser coverage on plans | Fire strategy diagrams | Compliance | Building Control | As-Built
Fire Strategy | Fire stopping at penetrations | Fire strategy / specification | Compliance | Warranty | As-Built
Spec vs Drawings | Wall build-ups on GA plans | Architectural specification | Coordination | Warranty | As-Built
Spec vs Drawings | Fire ratings on drawings | Specification | Compliance | Building Control / Warranty | As-Built
Spec vs Drawings | Acoustic ratings | Acoustic report | Compliance | Warranty | As-Built
Spec vs Drawings | Door ironmongery | Ironmongery specification | Coordination | Warranty | As-Built
As-Built / Handover | As-built drawings | Construction issue drawings | Compliance | Building Control / Warranty | As-Built
As-Built / Handover | O&M manuals | Asset schedules | Compliance | Warranty | As-Built
As-Built / Handover | Fire strategy (as-built) | Installed condition | Compliance | Building Control | As-Built
Fire Strategy | Fire compartment lines on GA plans | Fire strategy drawings | Compliance | Building Control / Warranty | As-Built
Fire Strategy | Fire door ratings on GA plans | Fire strategy report | Compliance | Building Control / Warranty | As-Built
Fire Strategy | Fire door ratings on door schedule | Fire strategy report | Compliance | Building Control / Warranty | As-Built
Fire Strategy | Fire door swing direction on GA plans | Fire strategy drawings | Compliance | Building Control | As-Built
Fire Strategy | Smoke shaft locations on GA plans | Smoke control strategy | Compliance | Building Control | As-Built
Fire Strategy | AOV free area on drawings | Smoke control calculations | Compliance | Building Control | As-Built
Fire Strategy | Dry riser coverage on plans | Fire strategy diagrams | Compliance | Building Control | As-Built
Fire Strategy | Fire stopping at penetrations | Fire strategy / specification | Compliance | Warranty | As-Built
Spec vs Drawings | Wall build-ups on GA plans | Architectural specification | Coordination | Warranty | As-Built
Spec vs Drawings | Fire ratings on drawings | Specification | Compliance | Building Control / Warranty | As-Built
Spec vs Drawings | Acoustic ratings | Acoustic report | Compliance | Warranty | As-Built
Spec vs Drawings | Door ironmongery | Ironmongery specification | Coordination | Warranty | As-Built
As-Built / Handover | As-built drawings | Construction issue drawings | Compliance | Building Control / Warranty | As-Built
As-Built / Handover | O&M manuals | Asset schedules | Compliance | Warranty | As-Built
As-Built / Handover | Fire strategy (as-built) | Installed condition | Compliance | Building Control | As-Built
Fire Strategy | Fire compartment lines on GA plans | Fire strategy drawings | Compliance | Building Control / Warranty | As-Built
Fire Strategy | Fire door ratings on GA plans | Fire strategy report | Compliance | Building Control / Warranty | As-Built
Fire Strategy | Fire door ratings on door schedule | Fire strategy report | Compliance | Building Control / Warranty | As-Built
Fire Strategy | Fire door swing direction on GA plans | Fire strategy drawings | Compliance | Building Control | As-Built
Fire Strategy | Smoke shaft locations on GA plans | Smoke control strategy | Compliance | Building Control | As-Built
Fire Strategy | AOV free area on drawings | Smoke control calculations | Compliance | Building Control | As-Built
Fire Strategy | Dry riser coverage on plans | Fire strategy diagrams | Compliance | Building Control | As-Built
Fire Strategy | Fire stopping at penetrations | Fire strategy / specification | Compliance | Warranty | As-Built
Spec vs Drawings | Wall build-ups on GA plans | Architectural specification | Coordination | Warranty | As-Built
Spec vs Drawings | Fire ratings on drawings | Specification | Compliance | Building Control / Warranty | As-Built
Spec vs Drawings | Acoustic ratings | Acoustic report | Compliance | Warranty | As-Built
Spec vs Drawings | Door ironmongery | Ironmongery specification | Coordination | Warranty | As-Built
As-Built / Handover | As-built drawings | Construction issue drawings | Compliance | Building Control / Warranty | As-Built
As-Built / Handover | O&M manuals | Asset schedules | Compliance | Warranty | As-Built
As-Built / Handover | Fire strategy (as-built) | Installed condition | Compliance | Building Control | As-Built
Fire Strategy | Fire compartment lines on GA plans | Fire strategy drawings | Compliance | Building Control / Warranty | As-Built
Fire Strategy | Fire door ratings on GA plans | Fire strategy report | Compliance | Building Control / Warranty | As-Built
Fire Strategy | Fire door ratings on door schedule | Fire strategy report | Compliance | Building Control / Warranty | As-Built
Fire Strategy | Fire door swing direction on GA plans | Fire strategy drawings | Compliance | Building Control | As-Built
Fire Strategy | Smoke shaft locations on GA plans | Smoke control strategy | Compliance | Building Control | As-Built
Fire Strategy | AOV free area on drawings | Smoke control calculations | Compliance | Building Control | As-Built
Fire Strategy | Dry riser coverage on plans | Fire strategy diagrams | Compliance | Building Control | As-Built
Fire Strategy | Fire stopping at penetrations | Fire strategy / specification | Compliance | Warranty | As-Built
Spec vs Drawings | Wall build-ups on GA plans | Architectural specification | Coordination | Warranty | As-Built
Spec vs Drawings | Fire ratings on drawings | Specification | Compliance | Building Control / Warranty | As-Built
Spec vs Drawings | Acoustic ratings | Acoustic report | Compliance | Warranty | As-Built
Spec vs Drawings | Door ironmongery | Ironmongery specification | Coordination | Warranty | As-Built
As-Built / Handover | As-built drawings | Construction issue drawings | Compliance | Building Control / Warranty | As-Built
As-Built / Handover | O&M manuals | Asset schedules | Compliance | Warranty | As-Built
As-Built / Handover | Fire strategy (as-built) | Installed condition | Compliance | Building Control | As-Built